## Cover
MicroLIMS
DOCUMENT CONTROL MODULE — REQUIREMENTS RISK ASSESSMENT
Document Title | MicroLIMS Document Control Module — Requirements Risk Assessment
Document Type | Risk Assessment (GAMP 5, Second Edition — risk-based approach)
Parent Documents | Project Charter v1.0; URS v1.0; URS Amendment v1.1
Requirement Baseline | URS v1.1 — DC-URS-001 to DC-URS-203 (203 requirements)
Version | 1.0 (Draft for Risk Assessment Team Review)
Status | Draft
Business Area | Quality Control — Microbiology
System Category | GAMP Category 5 — Bespoke / custom developed application
Prepared Date | 06-Aug-2026
Purpose | To assess each approved user requirement for GxP impact and risk, and to determine the level of design control and qualification testing required for each requirement.
IMPORTANT — HOW TO USE THIS DOCUMENT
• Risk assessment is a team exercise. The severity, probability and detectability values in this workbook are a proposed starting position prepared from the requirement text; they are NOT approved values.
• The risk assessment team (QC/Microbiology, Quality Assurance, System Owner, IT) shall review every row, agree or amend each rating, and record the rationale before the assessment is approved.
• Failure scenarios have been written per requirement where the requirement carries specific risk, and per category elsewhere. Category-level scenarios should be made requirement-specific during review.
• Risk Class and Risk Priority are calculated by formula from the Severity, Probability and Detectability columns. Change a rating and the class, priority, control strategy and test approach update automatically.
• The 'Team Comment / Rationale' column is provided for the review record and shall be completed for every requirement whose rating is changed from the proposed value.
• This assessment covers requirement risk only. It does not replace supplier assessment, infrastructure qualification, or process risk assessment.
Risk Assessment Approval
Role | Name | Signature | Date
System Owner
QC / Microbiology Representative
Quality Assurance
IT / Technical Representative

## Methodology
Risk Assessment Methodology
Two-step qualitative assessment in accordance with GAMP 5 (Second Edition), ISPE risk-based approach and ICH Q9 principles.
1. Severity — impact of the failure if it occurs
Rating | Definition
High | Failure could result in incorrect laboratory work, use of an unapproved or superseded procedure, loss or corruption of a GxP record, loss of attributability, or an inability to demonstrate compliance during inspection.
Medium | Failure could result in incomplete, delayed or misleading compliance information, requiring investigation and correction but not directly compromising a GxP record.
Low | Failure causes inconvenience or reduced usability with no impact on record integrity or compliance.
2. Probability — likelihood of the failure occurring in a bespoke (Category 5) application
Rating | Definition
High | Complex logic, multiple interacting states, date/time driven behaviour, concurrency, background processing, or bulk data handling.
Medium | Standard workflow, permission or file handling logic with moderate branching.
Low | Simple create/read/display logic or static configuration with limited branching.
3. Detectability — likelihood the failure is detected before it causes harm
Rating | Definition
High | Failure is immediately visible to the user, blocks the workflow, or is routinely detected by normal use or existing checks.
Medium | Failure is detectable through periodic review, reporting or supervisory checks, but not immediately.
Low | Failure is silent. The system continues to operate normally and the defect may only be discovered during inspection or investigation.
4. Risk Class = Severity x Probability
Severity | Probability High | Probability Medium | Probability Low
High | Class 3 | Class 3 | Class 2
Medium | Class 3 | Class 2 | Class 1
Low | Class 2 | Class 1 | Class 1
5. Risk Priority = Risk Class x Detectability
Risk Class | Detectability Low | Detectability Medium | Detectability High
Class 3 | High | High | Medium
Class 2 | High | Medium | Low
Class 1 | Medium | Low | Low
6. Control strategy and verification by Risk Priority
Risk Priority | Required Control Strategy | Verification Approach
High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed
Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing
Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification

## Risk Assessment
Risk ID | URS ID | Category | User Requirement | Req. Priority | GxP Impact | Potential Failure Scenario | Severity | Probability | Detectability | Risk Class | Risk Priority | Risk Control Strategy | Verification Approach | URS Verification Method | Residual Risk | Team Comment / Rationale
RA-001 | DC-URS-001 | General | The system shall provide a dedicated Document Control module within MicroLIMS. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-002 | DC-URS-002 | General | The system shall maintain a centralized Master Document Register for controlled documents. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-003 | DC-URS-003 | General | The system shall preserve the organization-issued Company Document Code as a separate field from the MicroLIMS system ID. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-004 | DC-URS-004 | General | The system shall automatically generate a unique permanent MicroLIMS Document ID for each Document Master. | Must | Yes | Duplicate or non-unique MicroLIMS Document ID issued, breaking record identity. | High | Low | High | 2 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-005 | DC-URS-005 | General | The MicroLIMS Document ID shall remain unchanged across all revisions of the same Document Master. | Must | Yes | MicroLIMS Document ID changes across revisions, breaking traceability of all linked records. | High | Low | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-006 | DC-URS-006 | General | Authorized users shall be able to search and filter documents by company code, MicroLIMS ID, title, type, department/section, owner, status, revision and dates. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | Low | Low | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-007 | DC-URS-007 | General | The system shall support configurable document types including SOP, Protocol, Work Instruction, Test Method, Specification, Form, Template, Policy, Guideline and Other. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-008 | DC-URS-008 | General | The system shall support configurable departments and sections for document ownership and classification. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-009 | DC-URS-009 | General | Each Document Master shall maintain title, document type, department/section, owner and applicable classification metadata. | Must | Yes | Document master metadata or identification incorrect, incomplete or not retrievable. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-010 | DC-URS-010 | General | The system shall clearly identify the current effective revision of each Document Master. | Must | Yes | Incorrect revision presented as current effective, leading to use of a superseded procedure. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-011 | DC-URS-011 | Registration & Migration | Authorized users shall be able to register a new controlled document. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-012 | DC-URS-012 | Registration & Migration | The system shall permit a document record to be saved as Draft before all final approval/effective-date information is available. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-013 | DC-URS-013 | Registration & Migration | The system shall support import of a document register from a structured file such as CSV or Excel. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-014 | DC-URS-014 | Registration & Migration | The system shall support migration of a document register together with corresponding controlled files. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-015 | DC-URS-015 | Registration & Migration | Migration shall provide a validation/matching step before records are committed to the controlled library. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-016 | DC-URS-016 | Registration & Migration | The import process shall identify missing files, duplicate/conflicting company codes, invalid dates and other validation errors. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-017 | DC-URS-017 | Registration & Migration | Authorized users shall be able to resolve or manually match files before final migration confirmation. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-018 | DC-URS-018 | Registration & Migration | Imported records without files shall be identifiable as File Pending. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-019 | DC-URS-019 | Registration & Migration | The system shall generate MicroLIMS Document IDs for successfully imported Document Masters. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-020 | DC-URS-020 | Registration & Migration | The system shall retain an audit record of import/migration execution and results. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-021 | DC-URS-021 | File Control | The system shall support storage of a controlled PDF for each applicable document revision. | Must | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-022 | DC-URS-022 | File Control | The system should support storage of a restricted editable source file such as DOCX for each applicable revision. | Should | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-023 | DC-URS-023 | File Control | The system shall associate files with the exact revision to which they belong. | Must | Yes | File associated with the wrong revision; user reads content that does not correspond to the revision they were assigned. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-024 | DC-URS-024 | File Control | The system shall prevent historical revision files from being overwritten through normal user functions. | Must | Yes | Historical revision file overwritten; original record irretrievably lost. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-025 | DC-URS-025 | File Control | The system shall prevent silent replacement of files belonging to an effective revision. | Must | Yes | Effective revision file silently replaced; no user-visible indication that controlled content changed. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-026 | DC-URS-026 | File Control | The system shall provide an integrated controlled PDF viewer for reading and review. | Must | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-027 | DC-URS-027 | File Control | The viewer shall display the document identity and revision being viewed. | Must | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | Low | Low | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-028 | DC-URS-028 | File Control | Access to source/editable files shall be permission-controlled. | Must | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-029 | DC-URS-029 | File Control | Controlled copy download/print behavior shall be configurable by authorized administrators. | Must | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-030 | DC-URS-030 | File Control | Superseded documents shall be clearly identified and access shall be controlled according to configured policy. | Must | Yes | Superseded document accessible without identification and used as current. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-031 | DC-URS-031 | Lifecycle | The system shall support statuses including Draft, Technical Review, Awaiting Approval, Approved, Future Effective, Effective, Superseded and Obsolete. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-032 | DC-URS-032 | Lifecycle | The system shall support return-for-correction and decline/rejection outcomes where appropriate. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-033 | DC-URS-033 | Lifecycle | An effective revision shall not be directly editable. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-034 | DC-URS-034 | Lifecycle | Changes to an effective document shall require creation of a new revision. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-035 | DC-URS-035 | Lifecycle | The system shall permit an effective revision and a future-effective approved revision to coexist for the same Document Master. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-036 | DC-URS-036 | Lifecycle | On the effective date, the system shall automatically set the approved future revision to Effective and the prior effective revision to Superseded. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-037 | DC-URS-037 | Lifecycle | Automatic lifecycle transitions shall be recorded in the audit trail. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-038 | DC-URS-038 | Lifecycle | The system shall clearly distinguish approval date from effective date. | Must | Yes | Document held in an incorrect lifecycle state; unapproved or superseded content available as current. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-039 | DC-URS-039 | Lifecycle | The system shall prevent more than one revision of the same Document Master from being Effective at the same time, except for explicitly configured exceptional migration states. | Must | Yes | Future-effective revision fails to activate on the effective date; superseded procedure remains in use. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-040 | DC-URS-040 | Lifecycle | The system shall retain complete lifecycle history for each revision. | Must | Yes | Prior revision not superseded on activation; two revisions appear effective simultaneously. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-041 | DC-URS-041 | Periodic Review | Each applicable document shall support a configurable review cycle and Review Due Date. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-042 | DC-URS-042 | Periodic Review | The system shall calculate the next review date according to the configured review cycle or authorized override. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-043 | DC-URS-043 | Periodic Review | The system shall provide configurable advance reminders for upcoming periodic reviews. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-044 | DC-URS-044 | Periodic Review | The system shall automatically create a Periodic Review task when the review becomes due. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-045 | DC-URS-045 | Periodic Review | The Periodic Review workspace shall display the actual controlled PDF being reviewed. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Low | Low | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-046 | DC-URS-046 | Periodic Review | The reviewer shall be able to record review notes linked to a page and/or section. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-047 | DC-URS-047 | Periodic Review | The reviewer shall select an outcome of Remains Valid, Revision Required, or Recommend Obsolescence. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-048 | DC-URS-048 | Periodic Review | A Remains Valid decision shall not create a new revision. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-049 | DC-URS-049 | Periodic Review | A Remains Valid decision shall create a review history record and calculate/set the next review due date. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-050 | DC-URS-050 | Periodic Review | A Revision Required decision shall permit initiation of a new revision linked to the originating Periodic Review. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-051 | DC-URS-051 | Periodic Review | Periodic Review findings shall be transferable into the new revision as required-change items. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-052 | DC-URS-052 | Periodic Review | A recommendation for obsolescence shall require a controlled approval process before the document becomes Obsolete. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-053 | DC-URS-053 | Periodic Review | Periodic Review history shall be maintained independently from Revision History. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-054 | DC-URS-054 | Periodic Review | Overdue periodic reviews shall be identifiable on dashboards/reports. | Must | Yes | Periodic review not scheduled, not triggered or outcome not recorded; document remains in use beyond its review period without assessment. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-055 | DC-URS-055 | Revision Control | Authorized users shall be able to create a new revision from an effective document. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-056 | DC-URS-056 | Revision Control | A new revision shall retain the same Document Master and MicroLIMS Document ID. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-057 | DC-URS-057 | Revision Control | The system shall propose the next revision number while allowing authorized adjustment where company numbering rules require it. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-058 | DC-URS-058 | Revision Control | Each revision shall record Reason for Revision and Change Summary. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-059 | DC-URS-059 | Revision Control | The system shall support a Change Reference field. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-060 | DC-URS-060 | Revision Control | The system should support Major/Minor revision classification. | Should | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-061 | DC-URS-061 | Revision Control | The system shall support structured affected-section/change items. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-062 | DC-URS-062 | Revision Control | The system shall support revision impact assessment categories including procedure/method, training, forms/templates, specifications, equipment, materials/media, validation, regulatory commitment, related documents and other. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-063 | DC-URS-063 | Revision Control | Originating Periodic Review findings shall be traceable from the revision. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-064 | DC-URS-064 | Revision Control | Before submission, each originating required-change finding shall be Addressed or have an authorized documented justification. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-065 | DC-URS-065 | Revision Control | The current effective revision shall remain available while the proposed revision is in Draft/Review/Approval. | Must | Yes | Revision created, numbered or linked incorrectly; change history incomplete or effective revision ambiguous. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-066 | DC-URS-066 | Review & Approval | Submitted revisions shall enter a controlled Technical Review workflow. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-067 | DC-URS-067 | Review & Approval | The reviewer shall be able to view the current effective revision and proposed revision side-by-side. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | High | Low | High | 2 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-068 | DC-URS-068 | Review & Approval | The reviewer shall be able to create page/section-specific review comments. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-069 | DC-URS-069 | Review & Approval | Review comments shall support at least Open, Author Response/Correction, Reviewer Verification and Resolved states. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-070 | DC-URS-070 | Review & Approval | The author shall not be able to close a reviewer-required comment without reviewer verification. | Must | Yes | Author closes a reviewer-required comment without verification; unresolved technical issue reaches approval. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-071 | DC-URS-071 | Review & Approval | Technical Review completion shall be blocked while mandatory review comments remain unresolved. | Must | Yes | Technical review completed with mandatory comments open. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-072 | DC-URS-072 | Review & Approval | The reviewer shall be able to Return for Correction or Complete Review/Recommend for Approval. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-073 | DC-URS-073 | Review & Approval | After completed technical review, the revision shall enter Awaiting Approval. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-074 | DC-URS-074 | Review & Approval | The approver shall be able to inspect the proposed controlled PDF, change summary, impact assessment, review history, comments/resolutions, effective date, training requirement and KAF configuration. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-075 | DC-URS-075 | Review & Approval | The approver shall be able to Approve, Return for Correction or Decline the revision. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-076 | DC-URS-076 | Review & Approval | Approval shall require authenticated electronic-signature confirmation when configured. | Must | Yes | Approval recorded without authenticated electronic signature. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-077 | DC-URS-077 | Review & Approval | The electronic-signature record shall capture signer identity, date/time, action/signature meaning, revision and applicable comment. | Must | Yes | Electronic signature record incomplete — signer, meaning, date/time or revision not captured. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-078 | DC-URS-078 | Review & Approval | The system shall prevent unauthorized users from performing reviewer or approver actions. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-079 | DC-URS-079 | Review & Approval | Approval and review actions shall be audit-trailed. | Must | Yes | Revision progresses to effective without completed technical review or authorised approval; approval record incomplete. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-080 | DC-URS-080 | Reading & Training | Controlled revisions shall support training requirements of Read Only, Read + Acknowledge, Read + KAF, or Read + Acknowledge + KAF. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-081 | DC-URS-081 | Reading & Training | Training requirements shall be configurable by document/revision and/or document type defaults. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-082 | DC-URS-082 | Reading & Training | Authorized users shall be able to assign training to individual users, roles, departments, sections or configured groups. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-083 | DC-URS-083 | Reading & Training | Every training assignment shall reference the exact document revision. | Must | Yes | Assignment references the wrong revision; training evidence attributed to content the user never read. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-084 | DC-URS-084 | Reading & Training | Users shall have a My Reading List showing assigned documents, revision, effective date, assignment date, due date, requirement, status and progress. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-085 | DC-URS-085 | Reading & Training | Users shall be able to open the assigned controlled PDF from the Reading List. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-086 | DC-URS-086 | Reading & Training | The system shall record reading/acknowledgement timestamps and the exact revision acknowledged. | Must | Yes | Acknowledgement recorded without the exact revision, or with an incorrect timestamp. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-087 | DC-URS-087 | Reading & Training | Acknowledgement shall require an explicit user action when configured. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-088 | DC-URS-088 | Reading & Training | The system shall identify overdue training assignments. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-089 | DC-URS-089 | Reading & Training | Authorized users shall be able to reassign training and send reminders. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-090 | DC-URS-090 | Reading & Training | The system shall retain historical training evidence after a newer document revision is issued. | Must | Yes | Historical training evidence lost or overwritten when a new revision is issued. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-091 | DC-URS-091 | Reading & Training | Phase 1 shall not automatically block laboratory execution activities based on training status. | Must | Yes | Personnel not assigned, or assigned to the wrong revision; training status misrepresented. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-092 | DC-URS-092 | KAF | The system shall support creation and management of Knowledge Assessment Forms (KAF). | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-093 | DC-URS-093 | KAF | A KAF shall be version-controlled. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-094 | DC-URS-094 | KAF | A KAF may be associated with a specific controlled document revision. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-095 | DC-URS-095 | KAF | Authorized users shall be able to copy a KAF from a previous document revision to create a new editable KAF version. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-096 | DC-URS-096 | KAF | Historical KAF versions and results shall remain unchanged when a new KAF version is created. | Must | Yes | Historical KAF versions or results altered when a new KAF version is created. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-097 | DC-URS-097 | KAF | KAF configuration shall support passing score and maximum attempts. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-098 | DC-URS-098 | KAF | KAF configuration should support open-book/closed-book mode and time limit. | Should | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-099 | DC-URS-099 | KAF | KAF configuration should support question and answer-option randomization. | Should | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-100 | DC-URS-100 | KAF | The system shall support Single Choice, Multiple Choice and True/False question types. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-101 | DC-URS-101 | KAF | The system should support scenario-based questions. | Should | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-102 | DC-URS-102 | KAF | Questions should support mapping/reference to an SOP/document section. | Should | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-103 | DC-URS-103 | KAF | The user assessment screen shall show question progress and navigation. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Low | Medium | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-104 | DC-URS-104 | KAF | Users shall be able to flag questions for review before submission. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | High | 2 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-105 | DC-URS-105 | KAF | Before final submission, the system shall identify unanswered and flagged questions. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | High | 2 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-106 | DC-URS-106 | KAF | The system shall automatically score objective questions. | Must | Yes | Objective questions scored incorrectly; pass/fail result invalid. | High | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-107 | DC-URS-107 | KAF | For each attempt, the system shall retain user, document revision, KAF version, attempt number, questions presented, responses, score, result, start time and submission/completion time. | Must | Yes | Attempt record incomplete; result not reconstructable or not attributable. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-108 | DC-URS-108 | KAF | The system shall enforce the configured maximum number of attempts. | Must | Yes | Configured maximum attempts not enforced. | Medium | Medium | High | 2 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-109 | DC-URS-109 | KAF | The system shall identify Pass and Fail results according to the configured passing score. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-110 | DC-URS-110 | KAF | KAF attempts/results shall be audit-trailed. | Must | Yes | Assessment configured, scored or attributed incorrectly; result not traceable to the exact document revision and KAF version. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-111 | DC-URS-111 | Training Matrix | Authorized users shall have access to a Training Matrix showing personnel against required document revisions. | Must | Yes | Training status displayed incorrectly, leading to an incorrect compliance conclusion. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-112 | DC-URS-112 | Training Matrix | Training states shall include Not Assigned, Assigned, Reading, Acknowledged, KAF Pending, Completed/Passed, Failed and Overdue as applicable. | Must | Yes | Training status displayed incorrectly, leading to an incorrect compliance conclusion. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-113 | DC-URS-113 | Training Matrix | The matrix shall support filtering by employee, department, role, document type, document, revision, status, requirement and due date. | Must | Yes | Training status displayed incorrectly, leading to an incorrect compliance conclusion. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-114 | DC-URS-114 | Training Matrix | Authorized users shall be able to open detailed training evidence from a matrix cell/record. | Must | Yes | Training status displayed incorrectly, leading to an incorrect compliance conclusion. | Medium | High | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-115 | DC-URS-115 | Training Matrix | Training evidence shall include assignment, reading/acknowledgement, KAF attempt/result and completion information as applicable. | Must | Yes | Training status displayed incorrectly, leading to an incorrect compliance conclusion. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-116 | DC-URS-116 | Reports & KPIs | The system shall provide Document Control dashboards and KPIs. | Must | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-117 | DC-URS-117 | Reports & KPIs | KPIs shall include Effective Documents, Reviews Due, Overdue Reviews, Revisions in Progress, Awaiting Approval, Training Compliance, Overdue Training and KAF Pass Rate. | Must | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Low | Medium | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-118 | DC-URS-118 | Reports & KPIs | The system should provide approval cycle time and technical review time metrics. | Should | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-119 | DC-URS-119 | Reports & KPIs | KPI cards/alerts should allow drill-down to underlying records. | Should | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | PQ/UAT | Low
RA-120 | DC-URS-120 | Reports & KPIs | The system shall provide a Master Document Register report. | Must | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-121 | DC-URS-121 | Reports & KPIs | The system shall provide Effective Document List, Revision History, Periodic Review Status, Training Compliance, Individual Training History, KAF Results, Overdue Assignments, Document Approval History and Audit Trail reports. | Must | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Medium | Medium | Low | 2 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-122 | DC-URS-122 | Reports & KPIs | Authorized users shall be able to export applicable reports according to permissions. | Must | Yes | Report or indicator returns incomplete or incorrect data used for compliance decisions. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-123 | DC-URS-123 | Audit Trail | The system shall maintain an audit trail for controlled Document Control activities. | Must | Yes | Controlled action occurs with no audit record created. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-124 | DC-URS-124 | Audit Trail | Audit events shall record date/time, user, action, record type, affected document/revision and event identifier. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-125 | DC-URS-125 | Audit Trail | Where applicable, audit events shall record previous value and new value. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-126 | DC-URS-126 | Audit Trail | Where applicable, audit events shall retain reason/comment and electronic-signature context. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-127 | DC-URS-127 | Audit Trail | Audit records shall be read-only through the normal application. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-128 | DC-URS-128 | Audit Trail | Audit records shall not be deletable through normal application functions. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-129 | DC-URS-129 | Audit Trail | Authorized users shall be able to search/filter the global audit trail by date range, user, document/company code, MicroLIMS ID, revision, record type and action category. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-130 | DC-URS-130 | Audit Trail | Each Document Master/revision shall provide access to its record-specific audit history. | Must | Yes | Controlled action not captured, captured incompletely, or alterable — loss of attributability and traceability. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-131 | DC-URS-131 | Audit Trail | The system shall audit document creation/import, metadata changes, file changes, revisions, submissions, review actions, approvals, effective/superseded transitions, periodic reviews, training, acknowledgements, KAF, configuration and relevant security/administrative actions. | Must | Yes | Audit record alterable or deletable through the application. | High | Low | Low | 2 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-132 | DC-URS-132 | Audit Trail | System-generated automatic status transitions shall identify the system context/source in the audit trail. | Must | Yes | Audit trail not retained for the required period or not retrievable. | High | Low | Low | 2 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-133 | DC-URS-133 | Configuration | Authorized administrators shall be able to configure document types. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-134 | DC-URS-134 | Configuration | Authorized administrators shall be able to configure departments/sections. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-135 | DC-URS-135 | Configuration | Authorized administrators shall be able to configure default review cycles. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-136 | DC-URS-136 | Configuration | Authorized administrators shall be able to configure the MicroLIMS Document ID prefix/numbering pattern. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-137 | DC-URS-137 | Configuration | The company document code shall not be automatically overwritten by the MicroLIMS numbering configuration. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-138 | DC-URS-138 | Configuration | Authorized administrators shall be able to configure workflow templates and applicable reviewer/approver roles. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-139 | DC-URS-139 | Configuration | Authorized administrators shall be able to configure training defaults and KAF defaults. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-140 | DC-URS-140 | Configuration | Authorized administrators shall be able to configure notifications and escalation intervals. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-141 | DC-URS-141 | Configuration | Authorized administrators shall be able to configure controlled-copy behavior and import/migration settings. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-142 | DC-URS-142 | Configuration | Configuration changes shall be audit-trailed. | Must | Yes | Configuration set incorrectly or changed without control, altering validated system behaviour. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-143 | DC-URS-143 | Security | The system shall use role-based access control for Document Control functions. | Must | Yes | Unauthorised user performs a controlled action; action attributed to the wrong identity. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-144 | DC-URS-144 | Security | Permissions shall distinguish at least administration, document control, authoring, technical review, approval, reading/training, compliance viewing and audit viewing functions. | Must | Yes | Unauthorised user performs a controlled action; action attributed to the wrong identity. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-145 | DC-URS-145 | Security | The system shall require authenticated user identity for controlled actions. | Must | Yes | Unauthorised user performs a controlled action; action attributed to the wrong identity. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-146 | DC-URS-146 | Security | The system shall prevent a user from performing actions for which the user lacks permission. | Must | Yes | Unauthorised user performs a controlled action; action attributed to the wrong identity. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-147 | DC-URS-147 | Security | Electronic-signature actions shall require re-authentication or equivalent validated signature confirmation according to approved system design. | Must | Yes | Electronic signature applied without re-authentication of the signer. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-148 | DC-URS-148 | Security | The system shall associate controlled actions with the authenticated user and date/time. | Must | Yes | Unauthorised user performs a controlled action; action attributed to the wrong identity. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-149 | DC-URS-149 | Data Integrity | The system shall preserve historical revisions, approvals, periodic reviews, training evidence and KAF results as enduring records. | Must | Yes | Record altered, lost or no longer traceable to its originating revision and user. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-150 | DC-URS-150 | Data Integrity | The system shall maintain traceability between Document Master, revision, controlled file, workflow records, training assignments and KAF records. | Must | Yes | Record altered, lost or no longer traceable to its originating revision and user. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-151 | DC-URS-151 | Data Integrity | Date/time stamps shall be generated consistently by the system and stored in a controlled manner. | Must | Yes | Inconsistent or user-influenced timestamps; contemporaneity of records cannot be demonstrated. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-152 | DC-URS-152 | Data Integrity | The system shall not permit normal users to alter audit trail records. | Must | Yes | Normal user able to alter audit trail records. | High | Low | Low | 2 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-153 | DC-URS-153 | Data Integrity | The system shall identify the exact revision associated with every approval, acknowledgement, training completion and KAF attempt. | Must | Yes | Approval, acknowledgement or assessment record not linked to the exact revision. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-154 | DC-URS-154 | Data Integrity | The system shall provide records in a form that is legible and retrievable for authorized review. | Must | Yes | Record altered, lost or no longer traceable to its originating revision and user. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-155 | DC-URS-155 | Data Integrity | The system shall support backup/restore and retention through the validated MicroLIMS infrastructure. | Must | Yes | Backup or restore fails; controlled records unrecoverable. | High | Low | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | INS | Low
RA-156 | DC-URS-156 | Usability | The interface shall clearly display document status, revision and effective-date information. | Must | No | Information presented unclearly, increasing the likelihood of user error. | Low | Low | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-157 | DC-URS-157 | Usability | Validation/readiness indicators should identify missing mandatory information before submission. | Should | No | Information presented unclearly, increasing the likelihood of user error. | Low | Medium | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | PQ/UAT | Low
RA-158 | DC-URS-158 | Usability | The system should provide notifications for assigned reviews, approvals, reading/training and overdue activities. | Should | No | Information presented unclearly, increasing the likelihood of user error. | Low | Medium | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | PQ/UAT | Low
RA-159 | DC-URS-159 | Performance | Common Document Library searches and record opening should complete within an acceptable validated response time under expected load. | Should | No | Slow response degrades usability; no direct record impact. | Low | Medium | High | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | PQ/UAT | Low
RA-160 | DC-URS-160 | Availability | The module shall use the established MicroLIMS application availability, backup, recovery and access infrastructure. | Must | Yes | System or records unavailable when required for review or inspection. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | INS | Low
RA-161 | DC-URS-161 | Scope Boundary | Phase 1 shall not automatically inject controlled documents into laboratory testing workspaces. | Must | Yes | Phase 1 module unintentionally influences laboratory execution outside the validated scope. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-162 | DC-URS-162 | Scope Boundary | Phase 1 shall not automatically block laboratory execution because an analyst has not completed document training. | Must | Yes | Phase 1 module unintentionally influences laboratory execution outside the validated scope. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-163 | DC-URS-163 | Scope Boundary | Future workspace integration shall be treated as a separate controlled project/change because it affects multiple MicroLIMS modules. | Must | Yes | Phase 1 module unintentionally influences laboratory execution outside the validated scope. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-164 | DC-URS-164 | Segregation of Duties | The author of a document revision shall not be able to perform the technical review of that same revision. | Must | Yes | Same individual authors, reviews and approves a revision; independence of review and approval is lost and the defect is not visible in the record. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-165 | DC-URS-165 | Segregation of Duties | The technical reviewer of a document revision shall not be able to perform the final approval of that same revision. | Must | Yes | Same individual authors, reviews and approves a revision; independence of review and approval is lost and the defect is not visible in the record. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-166 | DC-URS-166 | Segregation of Duties | Segregation-of-duties restrictions shall be enforced by the system and shall not be bypassable by any role, including System Administrator. | Must | Yes | System Administrator able to bypass segregation of duties; independence of approval defeated with no visible indication. | High | Low | Low | 2 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-167 | DC-URS-167 | Segregation of Duties | Where a user holds more than one functional role, the system shall prevent that user from performing conflicting controlled actions on the same document revision. | Must | Yes | Same individual authors, reviews and approves a revision; independence of review and approval is lost and the defect is not visible in the record. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-168 | DC-URS-168 | Segregation of Duties | Each Document Master shall identify its Document Owner, designated Technical Reviewer(s) and designated Approver(s), and controlled workflow authority shall be derived from these assignments in addition to role permissions. | Must | Yes | Same individual authors, reviews and approves a revision; independence of review and approval is lost and the defect is not visible in the record. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-169 | DC-URS-169 | Segregation of Duties | An attempt to perform a controlled action that violates segregation of duties shall be rejected and recorded in the audit trail. | Must | Yes | Same individual authors, reviews and approves a revision; independence of review and approval is lost and the defect is not visible in the record. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-170 | DC-URS-170 | Training Cascade | When a new revision becomes effective, the system shall automatically create training assignments for the personnel population that was assigned the previous effective revision, where configured for the document or document type. | Must | Yes | Re-training not issued when a revision becomes effective; personnel remain qualified only on superseded content. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-171 | DC-URS-171 | Training Cascade | The requirement for re-reading and/or re-assessment on a new revision shall be configurable at document type level with override at document/revision level. | Must | Yes | Personnel continue working to a superseded revision because re-training was not issued, or historical evidence is lost or overwritten. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-172 | DC-URS-172 | Training Cascade | Incomplete training assignments against a revision that becomes superseded shall be closed with a distinct terminal status indicating non-completion, and shall be retained as records rather than deleted. | Must | Yes | Incomplete assignments deleted rather than closed and retained; evidence of non-completion lost. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-173 | DC-URS-173 | Training Cascade | Completed training and assessment records against a superseded revision shall remain unchanged and retrievable. | Must | Yes | Personnel continue working to a superseded revision because re-training was not issued, or historical evidence is lost or overwritten. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-174 | DC-URS-174 | Training Cascade | The system shall identify personnel who are trained on a superseded revision but have not yet completed training on the current effective revision. | Must | Yes | Personnel continue working to a superseded revision because re-training was not issued, or historical evidence is lost or overwritten. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-175 | DC-URS-175 | Training Cascade | When a document becomes Obsolete, open training assignments for that document shall be cancelled with a recorded reason, and existing completed evidence shall be retained. | Must | Yes | Personnel continue working to a superseded revision because re-training was not issued, or historical evidence is lost or overwritten. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-176 | DC-URS-176 | Training Cascade | Where a Knowledge Assessment is failed and re-training is configured, the system shall re-issue the assignment in accordance with the configured re-training rule and retain all prior attempts. | Must | Yes | Personnel continue working to a superseded revision because re-training was not issued, or historical evidence is lost or overwritten. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-177 | DC-URS-177 | Automatic System Actions | The system shall automatically transition an approved Future Effective revision to Effective on its configured effective date without user intervention. | Must | Yes | Date-driven transition does not execute, executes at the wrong time, or executes without traceable attribution — silent failure with no user prompt. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-178 | DC-URS-178 | Automatic System Actions | On automatic activation of a new effective revision, the system shall automatically set the previous effective revision to Superseded. | Must | Yes | Date-driven transition does not execute, executes at the wrong time, or executes without traceable attribution — silent failure with no user prompt. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-179 | DC-URS-179 | Automatic System Actions | The system shall automatically create Periodic Review tasks and issue configured advance notifications based on the Review Due Date. | Must | Yes | Date-driven transition does not execute, executes at the wrong time, or executes without traceable attribution — silent failure with no user prompt. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-180 | DC-URS-180 | Automatic System Actions | Automatic system actions shall be recorded in the audit trail and attributed to the system rather than to a named user, with the triggering rule identified. | Must | Yes | Date-driven transition does not execute, executes at the wrong time, or executes without traceable attribution — silent failure with no user prompt. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-181 | DC-URS-181 | Automatic System Actions | If a scheduled automatic action does not execute at its due time due to system unavailability, the system shall execute the outstanding action on the next successful run, record the actual execution time, and identify the action as a delayed execution. | Must | Yes | Scheduled transition missed during downtime and never executed; document lifecycle silently stalls. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-182 | DC-URS-182 | Automatic System Actions | All date-driven controlled transitions shall be evaluated against a single defined system time zone, and that time zone shall be documented and configurable only by authorized administrators. | Must | Yes | Time zone inconsistency causes a transition to occur on the wrong calendar day. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-183 | DC-URS-183 | Automatic System Actions | Failure of a scheduled automatic process shall be recorded and notified to authorized administrators. | Must | Yes | Date-driven transition does not execute, executes at the wrong time, or executes without traceable attribution — silent failure with no user prompt. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-184 | DC-URS-184 | Record Cancellation | No controlled document record, revision, workflow record, training record, assessment record or audit record shall be permanently deleted through the application by any user. | Must | Yes | Controlled record permanently deleted; loss of a GxP record with no recovery route. | High | Low | Low | 2 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-185 | DC-URS-185 | Record Cancellation | A draft revision that is no longer required shall be cancellable with a mandatory recorded reason, and shall be retained in read-only form. | Must | Yes | Controlled record deleted or removed without reason, authorisation or audit evidence. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-186 | DC-URS-186 | Record Cancellation | A Document Master registered in error shall be voidable with a mandatory recorded reason and appropriate authorization; the assigned MicroLIMS Document ID shall not be reused. | Must | Yes | Controlled record deleted or removed without reason, authorisation or audit evidence. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-187 | DC-URS-187 | Record Cancellation | Cancelled and voided records shall be excluded from the active document register and active work lists, while remaining retrievable by authorized users. | Must | Yes | Controlled record deleted or removed without reason, authorisation or audit evidence. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-188 | DC-URS-188 | Record Cancellation | Cancellation and voiding actions shall record the performing user, date/time and reason, and shall be audit-trailed. | Must | Yes | Controlled record deleted or removed without reason, authorisation or audit evidence. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-189 | DC-URS-189 | Reading Evidence | Explicit user acknowledgement, and where applicable a passed Knowledge Assessment, shall constitute the controlled evidence of reading completion. | Must | Yes | Training completion recorded without valid evidence, or acknowledgement recorded against the wrong revision. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-190 | DC-URS-190 | Reading Evidence | Any reading progress indicator presented to the user shall be informational only and shall not be used as an acceptance criterion for training completion. Where the organization requires a progress-based control, it shall be defined as an explicit configured acceptance criterion and validated as such. | Must | Yes | Progress metric used implicitly as an acceptance criterion without validation, or treated as evidence in an inspection. | Medium | Medium | Medium | 2 | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | OQ | Low
RA-191 | DC-URS-191 | Reading Evidence | The acknowledgement statement text shall be configurable and the exact statement text presented shall be retained with the acknowledgement record. | Must | Yes | Training completion recorded without valid evidence, or acknowledgement recorded against the wrong revision. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-192 | DC-URS-192 | Reading Evidence | The system shall not permit acknowledgement of a document revision other than the revision assigned and displayed to the user. | Must | Yes | Training completion recorded without valid evidence, or acknowledgement recorded against the wrong revision. | High | Low | High | 2 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-193 | DC-URS-193 | Registration & Migration | Every Document Master, revision and training/assessment record shall carry an origin indicator distinguishing records created within MicroLIMS from records migrated from legacy systems or paper. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-194 | DC-URS-194 | Registration & Migration | Migrated records shall retain a reference to the migration batch identifier, source register/file reference, migration date and the user who performed the migration. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | High | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-195 | DC-URS-195 | Registration & Migration | On completion of a migration run, the system shall produce a reconciliation report identifying records submitted, imported, imported with warnings, rejected, and the file-matching outcome for each record. | Must | Yes | Migration completes without reconciliation; unnoticed record loss or mismatch between legacy register and MicroLIMS. | High | Medium | Medium | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-196 | DC-URS-196 | Registration & Migration | Migration reconciliation reports shall be retained and retrievable as data-migration verification evidence. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | INS | Medium (to be confirmed after test execution)
RA-197 | DC-URS-197 | Registration & Migration | Migrated historical training and assessment evidence shall be clearly identified as legacy evidence and shall not be presented as having been generated within MicroLIMS. | Must | Yes | Controlled document registered or migrated with incorrect identity, revision or file association; legacy record indistinguishable from a native record. | Medium | High | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-198 | DC-URS-198 | File Control | The system shall generate and store a cryptographic checksum for each controlled file at the point of upload. | Must | Yes | No integrity control on stored files; corruption or substitution undetectable. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-199 | DC-URS-199 | File Control | The system shall verify the stored checksum when a controlled file is retrieved and shall prevent or flag delivery of a file whose integrity cannot be confirmed. | Must | Yes | Corrupted or substituted file delivered to the user as a controlled copy. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-200 | DC-URS-200 | File Control | File upload, checksum generation and any detected integrity mismatch shall be recorded in the audit trail. | Must | Yes | Wrong, altered or superseded file served as the controlled copy without detection. | High | Medium | Low | 3 | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | OQ | Medium (to be confirmed after test execution)
RA-201 | DC-URS-201 | Integration Readiness | The system shall provide a controlled internal capability to return the current effective revision of a specified controlled document. | Must | Yes | Interface returns an incorrect effective revision or qualification status, or is consumed outside the approved Phase 1 scope. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-202 | DC-URS-202 | Integration Readiness | The system shall provide a controlled internal capability to return the training and assessment status of a specified user for a specified controlled document. | Must | Yes | Interface returns an incorrect effective revision or qualification status, or is consumed outside the approved Phase 1 scope. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low
RA-203 | DC-URS-203 | Integration Readiness | In Phase 1 these capabilities shall not be invoked by, and shall not influence, laboratory execution workflows; their use shall be introduced only through the separate future controlled project. | Must | Yes | Interface returns an incorrect effective revision or qualification status, or is consumed outside the approved Phase 1 scope. | Medium | Low | Medium | 1 | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | OQ | Low

## Lookups
Lookup tables — do not edit. Drive the calculated columns on the Risk Assessment sheet.
| Severity¦Probability | Risk Class | Class¦Detectability | Risk Priority | Risk Priority | Control Strategy | Verification Approach | Residual Risk
| High¦High | 3 | 3¦Low | High | High | Design control plus independent verification. Specify explicitly in the Functional/Design Specification, implement with backend enforcement, and challenge in OQ with positive and negative test cases. Supporting procedural control (SOP) required where residual risk remains. | Individual OQ test case — positive and negative testing, executed and witnessed | Medium (to be confirmed after test execution)
| High¦Medium | 3 | 3¦Medium | High | Medium | Specify in the Functional Specification and verify by individual OQ test case (positive testing). Procedural control where user judgement is involved. | Individual OQ test case — positive testing | Low
| High¦Low | 2 | 3¦High | Medium | Low | Verify by grouped OQ execution or PQ/UAT scenario. No additional design control required beyond standard development and code review. | Grouped OQ / PQ-UAT scenario verification | Low
| Medium¦High | 3 | 2¦Low | High
| Medium¦Medium | 2 | 2¦Medium | Medium
| Medium¦Low | 1 | 2¦High | Low
| Low¦High | 2 | 1¦Low | Medium
| Low¦Medium | 1 | 1¦Medium | Low
| Low¦Low | 1 | 1¦High | Low

## Summary
Risk Assessment Summary
All figures are formula-driven from the Risk Assessment sheet and update when ratings are amended.
Requirements by Risk Priority
Risk Priority | Count | % of Baseline | Verification Approach
High | 95 | 46.8% | Individual OQ test case — positive and negative testing, executed and witnessed
Medium | 75 | 36.95% | Individual OQ test case — positive testing
Low | 33 | 16.26% | Grouped OQ / PQ-UAT scenario verification
Total | 203 | 100%
Requirements by Category and Risk Priority
Category | Total | High | Medium | Low
Audit Trail | 10 | 6 | 3 | 1
Automatic System Actions | 7 | 7 | 0 | 0
Availability | 1 | 0 | 1 | 0
Configuration | 10 | 2 | 8 | 0
Data Integrity | 7 | 4 | 3 | 0
File Control | 13 | 7 | 3 | 3
General | 10 | 2 | 3 | 5
Integration Readiness | 3 | 0 | 0 | 3
KAF | 19 | 6 | 8 | 5
Lifecycle | 10 | 6 | 4 | 0
Performance | 1 | 0 | 0 | 1
Periodic Review | 14 | 4 | 9 | 1
Reading & Training | 12 | 5 | 6 | 1
Reading Evidence | 4 | 1 | 1 | 2
Record Cancellation | 5 | 5 | 0 | 0
Registration & Migration | 15 | 13 | 1 | 1
Reports & KPIs | 7 | 1 | 4 | 2
Review & Approval | 14 | 6 | 7 | 1
Revision Control | 11 | 2 | 9 | 0
Scope Boundary | 3 | 0 | 0 | 3
Security | 6 | 5 | 1 | 0
Segregation of Duties | 6 | 4 | 2 | 0
Training Cascade | 7 | 6 | 0 | 1
Training Matrix | 5 | 3 | 2 | 0
Usability | 3 | 0 | 0 | 3
Total | 203 | 95 | 75 | 33
Estimated Qualification Effort
Verification Approach | Requirements | Indicative OQ/PQ Test Cases | Basis
Individual OQ — positive and negative | 95 | 190 | Each high-risk requirement requires at least one positive and one negative test case.
Individual OQ — positive | 75 | 75 | One test case per requirement.
Grouped OQ / PQ-UAT | 33 | 9 | Approximately four low-risk requirements verified per grouped scenario.
Total | 203 | 274
Note: test case counts are indicative planning figures only and are superseded by the approved OQ/PQ protocols.